## Workplan 2022 Q1-Q2
Protection Cluster Mozambique - Action Plan/Focal Points and Distribution of Tasks
2022 (updated as of 3 Jan 2022)
# | UNIT | OBJECTIVE | COP 2018 /HRP 2018 | PROJECT | SPECIFIC | ACTIVITY (if applicable) | FREQUENCY | STATUS PROCESS | OUTPUT (n# / %) | FOCAL POINT (Name) |  | DEADLINE (Date) | PRIORITY (Low/Med/High) | PARTNERS (NGO/UN) | Q1 | [89 empty] | Q2
[15 empty] | JANUARY | [30 empty] | FEBRUARY | [27 empty] | MARCH | [30 empty] | APRIL | [29 empty] | MAY | [30 empty] | JUNE
[15 empty] | 1 | [6 empty] | 2 | [6 empty] | 3 | [6 empty] | 4 | [6 empty] | 5 | [6 empty] | 6 | [6 empty] | 7 | [6 empty] | 8 | [6 empty] | 9 | [6 empty] | 10 | [6 empty] | 11 | [6 empty] | 12 | [6 empty] | 13 | [5 empty] | 14 | [6 empty] | 15 | [6 empty] | 16 | [6 empty] | 17 | [6 empty] | 18 | [6 empty] | 19 | [6 empty] | 20 | [6 empty] | 21 | [6 empty] | 22 | [6 empty] | 23 | [6 empty] | 24 | [6 empty] | 25 | [6 empty] | 26
[10 empty] | Main | Back up |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
1 | Coordination Meetings |  |  | General Coordination | Protection Coordination Meetings | Coordination Meetings at National Level (Maputo) | Once Monthly |  | 12 Meetings
[6 empty] | Strategic Advisory Group PC Meetings (Hybrid: capital and field) | Once Monthly |  | 12 Meetings
[6 empty] | National level Ad Hoc Meetings (Maputo) | ad hoc
[6 empty] | Coordination Meetings at Pemba Level | Twice Monthly |  | 24 Meetings
[6 empty] | Pemba level Ad Hoc Meetings | ad hoc
[6 empty] | Coordination Meetings at Nampula Level | Twice Monthly |  | 24 Meetings
[6 empty] | Nampula level Ad Hoc Meetings | ad hoc
[5 empty] | Other coordination engagements | Bilateral engagements with other Clusters | ad hoc |  | 12 Meetings
[6 empty] | Bilateral engagements with development actors | ad hoc |  | 6 Meetings
|  |  |  | District Coordination Meetings | District Coordination Meeting | Montepuez (overnight), Metuge, Chiure and Mueda | Monthly?
[6 empty] | Chiure and Montepuez (January) | Monthly?
[6 empty] | Metuge and Mueda (February) | Monthly?
2 | Protection Monitoring |  |  | Inter-Agency Missions | Missions spear-headed by OCHA (with PC participation) | Protection Monitoring Mission | Once Monthly |  | 12 Missions
[6 empty] | Protection Cluster Mission Report | Once Monthly |  | 12 Mission Reports
|  |  |  | Protection Cluster Joint Field Missions | Missions with other PC Members | Protection Monitoring Mission | Once Monthly |  | 12 Missions
[6 empty] | Protection Cluster Mission Report | Once Monthly |  | 12 Mission Reports
|  |  |  | Protection Incident Monitoring System | Protection Incident Monitoring System | Establish PIMS with UNHCR, UNICEF, UNFPA | n/a |  | 1 System
[5 empty] | SOP Protection Incident Monitoring Tool | To write | n/a |  | 1 SOP
|  |  |  | Other Protection Monitoring Tools | IDP District Protection Profiles | District Profiles Montepuez | n/a |  | 1 per District
[6 empty] | District Profiles Metuge | n/a |  | 1 per District
[6 empty] | District Profiles Chiure | n/a |  | 1 per District
[6 empty] | District Profiles Ancuabe | n/a |  | 1 per District
[6 empty] | District Profiles Mueda | n/a |  | 1 per District
[5 empty] | IDP Intention Survey at Centro Desportivo | To do one once a month | Monthly |  | Update Monthly
[5 empty] | Mission Individual Protection Assessment Tool (non-border) | To finalize tool (and update regularly) | Each IA Mission |  | 1 per mission
2 | Trainings |  |  | Protection Trainings (including protection mainstreaming, GBV, CP, referrals, PSEA…) | Protection Training: PWG Nampula | Training for all PWG Members | Once Yearly |  | 1 Training
[5 empty] | Protection Training: PC Cabo Delgado | Training for all Cabo Delgado PC Members | Once Yearly |  | 1 Training
[5 empty] | Protection Training: PWG Sofala | Training for all PWG Sofala Members | Once Yearly |  | 1 Training
[5 empty] | Protection Mainstreaming Best Practices Mozambique | Collect Best Practices from Cluster Members | Once Yearly |  | 1 Fact Sheet
[5 empty] | Protection Mainstreaming/Training: Other clusters | Shelter/NFI | Once Yearly |  | 1 Training
[6 empty] | CCCM | Once Yearly |  | 1 Training
[6 empty] | WASH | Once Yearly |  | 1 Training
[6 empty] | Health | Once Yearly |  | 1 Training
[6 empty] | Education | Once Yearly |  | 1 Training
[6 empty] | Nutrition | Once Yearly |  | 1 Training
[6 empty] | Food Security and Livelihoods | Once Yearly |  | 1 Training
[5 empty] | Protection Mainstreaming/Training: Authorities | INGD Safeguarding Department - National Level | Once Yearly |  | 2 Trainings
[6 empty] | INGD Safeguarding Department - Provincial Level | Once Yearly |  | 2 Trainings
[6 empty] | Sofala | Once Yearly |  | 1 Training
[6 empty] | National Human Rights Commission | Once Yearly |  | 1 Training
[6 empty] | MGCAS/DPGCAS | Once Yearly |  | 1 Training
[5 empty] | Community Leaders Trainings | Community Leaders in District of Ancuabe | Once Yearly |  | 1 Workshop
[6 empty] | Community Leaders in District of Mueda | Once Yearly |  | 1 Workshop
[6 empty] | Community Leaders in District of Mecufi | Once Yearly |  | 1 Workshop
[6 empty] | Community Leaders in District of Pemba | Once Yearly |  | 1 Workshop
[5 empty] | Community Police Training | ? |  |  | 1 Training
[6 empty] | ? |  |  | 1 Training
3 | Strengthening Services |  |  | Strengthen Protection Referrals | Finalize Service Mapping and Referral Pathways | Cabo Delgado Service Mapping/Referral Pathways Montepuez | Once Yearly | Done | 1 Referral Pathway
[6 empty] | Cabo Delgado Service Mapping/Referral Pathways Metuge | Once Yearly |  | 1 Referral Pathway
[6 empty] | Cabo Delgado Service Mapping/Referral Pathways Chiure | Once Yearly |  | 1 Referral Pathway
[6 empty] | Cabo Delgado Service Mapping/Referral Pathways Ancuabe | Once Yearly |  | 1 Referral Pathway
[6 empty] | Cabo Delgado Service Mapping/Referral Pathways Mueda | Once Yearly |  | 1 Referral Pathway
[6 empty] | Nampula Service Mapping/Referral Pathways Corrane | Once Yearly | Done | 1 Referral Pathway
[6 empty] | Nampula Service Mapping/Referral Pathways Nampula City | Once Yearly |  | 1 Referral Pathway
[6 empty] | Niassa Service Mapping/Referral Pathways (?) | Once Yearly |  | 1 Referral Pathway
|  |  |  | Inter-Agency Referral Form | Mainstream Inter-agency referral form | Use harmonized for Cabo Delgado, Nampula and Niassa | n/a |  | 1 Referral Form
[6 empty] | Training on use of harmonized inter-agency form | Twice Yearly |  | 2 Workshops
4 | Partnerships |  |  | National Partners | National Human Rights Institutions | Frequent Meetings with Mozambican Human Rights Commission | Once Quarterly |  | Four briefings
[5 empty] | Increase National Partners in Cluster | Include Human Rights Commission in Protection Cluster Meetings | n/a |  | 1 Rep in PC Meeting
[6 empty] | Identify new national NGOs to participate in Cluster meetings | Continuous |  | 2 new nNGO
[6 empty] | Idnetify new national NGOs to be included in the 2023 HRP | Continuous |  | 2 new nNGO
|  |  |  | AoR and WG | Disability Working Group | Maintain leadership and participation | Continuous
[5 empty] | CP AoR | Maintain leadership and participation | Continuous
[5 empty] | GBV AoR | Maintain leadership and participation | Continuous
[5 empty] | HLP AoR | Maintain leadership and participation | Continuous
[5 empty] | CE/AAP | Maintain participation | Continuous
[5 empty] | Registration WG | Maintain participation | Continuous
[5 empty] | PSEA Network | Maintain participation | Continuous
[5 empty] | KC Domestication TWG | Maintain participation | Continuous
|  |  |  | National Authorities | MinGCAS | Strengthen Partnership and cooperation | Continuous
[5 empty] | DPGCAS Sofala | Strengthen Partnership and cooperation | Continuous
[5 empty] | DPGCAS Nampula | Strengthen Partnership and cooperation | Continuous
[5 empty] | DPGCAS Cabo Delgado | Strengthen Partnership and cooperation | Continuous
[5 empty] | INGD Sofala | Strengthen Partnership and cooperation | Continuous
[5 empty] | INGD Nampula | Strengthen Partnership and cooperation | Continuous
[5 empty] | INGD Cabo Delgado | Strengthen Partnership and cooperation | Continuous
5 | Reports |  |  | Regular External Update | Monthly PC National Update | Quarterly (possibility of scaling up monthly) | Quarterly |  | Four Quartlerly PC Updates
[5 empty] | Flash Report (Email Flash Updates) | Monthly | Monthly |  | 12 Flash Reports
|  |  |  | Internal Updates | Update GPC Internal Site | Monthly | Monthly |  | Monthly
|  |  |  | Briefing Notes | Thematic Protection Briefing Notes | Four thematic Briefing Notes on specific thematics | Four |  | Four Briefing Notes
|  |  |  | Key Messages | General Protection Key Messages | Update General Protection Key Messages | Update twice |  | Two Protection Key Messages
|  |  |  | Protection Analysis | Protection Brief (Protection Cluster) | Twice until end of year | Bi-Yearly |  | Two Protection Briefs
6 | Advocacy | Objective: Continuously engage with various donors in order to ensure funds are made available to UNHCR. | In 2018, the Office shall continue donor missions to the field, conduct briefings, disseminate relevant information, and to involve donors as much as possible in on-going strategic reflexions. One way of involving donor headquarters would be to also organise missions for the respected Desk Officers of Ministries of Foreign Affairs and visits of the Representative to donor capitals, which was initiated with a mission to Brussels at the end of 2016. Other capitals that could be interesting are Washington DC, Ottawa, Berlin, and Scandinavian capitals. (Page 5) | Engagement with Human Rights | Human Rights Engagements | Briefings to human rights advocates | Bi-Montly |  | SIX Briefings a year
[6 empty] | Diplomatic Briefing with OHCHR on human rights | Bi-Montly |  | SIX Briefings a year
[5 empty] | Human Rights Committee | Brefings to the National Human Rights Commission (with OHCHR) | Quarterly |  | FOUR Briefings
[6 empty] | Joint Field Mission with NHRC (with OHCHR) | Twice Yearly |  | TWO Field Missions
[5 empty] | Special Procedures Mandate Holders | Briefing SR on Human Rights of IDPs (with OHCHR) | Twice Yearly |  | Two Briefings
[5 empty] | Capacity building on human rights | Conduct trainings on Human Rights and other related topics
|  |  |  | Diplomatic Community | Donor Briefings | General briefing on Protection | Quarterly |  | FOUR Donor Briefings
[6 empty] | Thematic | ad hoc |  | ad hoc
[6 empty] | Donor Field Missions | Twice Yearly |  | TWO Field Missions
|  |  |  | UN Coordination | ICCG Briefings | Prepare briefings to ICCG (with PowerPoint/Update) | Bi-Montly |  | 24 Briefings
[5 empty] | HCT Briefings | Prepare briefings to ICCG (with PowerPoint/Update) | Bi-Montly |  | whenever invited
|  |  |  | Authorities | National Armed Forces | National
Cabo Delgado
[5 empty] | INGD (including Safeguarding Department) | National | Quarterly |  | FOUR Briefings
Nampula
[5 empty] | MGCAS (and DPGACS) | National (MGCAS) | Quarterly |  | FOUR Briefings
Cabo Delgado (DPGCAS)
Nampula (DPGCAS)
Sofala (DPGCAS)
|  |  | The Office shall continue to liaise with PSP on strengthening partnerships with existing private donors, reach out to potential private donors, and to expand existing campaigns, like the ‘Shelter campaign’. The Office will not invest in working with small, short-term donors, avoiding, for example, the high transaction costs and relatively low impact of receiving in-kind donations from private donors. Instead it will invest in multi-year and long term partnership with companies and the private sector. (Page 5) |  | State Secretary | Cabo Delgado
Nampula
Note on E7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Protection cluster (including AoR) meetings SAG meetings
Note on E16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Protection cluster (including AoR) meetings
Note on E32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Conduct training on protection mainstreaming and centrality of protection Conduct community based trainings on protection principles
Note on G86: Hugo Reichenberger: Ideas: BN: Humanitarian Access; BN: Vulnerability Criteria; BN: Civil Documentation (including Registration); BN: Persons with Disabilities; BN: Cholera and Protection; BN: Access to Education
Note on G89: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Briefings to and exchanges with partners (civil society, government actors) on human rights related topics
Note on G91: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Briefings to and exchanges with partners (civil society, government actors) on human rights related topics
Note on G92: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Coordination and engagement with human rights agencies, mechanisms and actors
Note on G93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Coordination and engagement with human rights agencies, mechanisms and actors